## Comparison
VERIDEX — CODEBASE COMPARISON & MERGE PLAN (Veridex = Source of Truth) — CONSOLIDATED v2 (Home-First + Full Figma UI)
Vercel: github.com/Abdurrahman99max/Veridex • Figma: github.com/Abdurrahman99max/Veridexapp • Target: Desktop/Veridex System • Updated: 2026-09-17 15:00 • Live: veridex-five.vercel.app & veridexapp.figma.site • Commits: c158e63→33dfdc0→63155de→3b9e97e→cde6f34
Category | Feature / Aspect | Veridex (Source of Truth) — Vercel | Veridexapp (Figma Make) — Figma Site | Merge Decision (Keep / Adopt / Merge) | Priority / Notes
STACK | Framework | Vite 6.3.5 + React 18.3.1, Tailwind 4.1.12, @tailwindcss/vite | Vite 6.3.5 + React 18.3.1, Tailwind 4.1.12, same plugin | KEEP Veridex stack (identical) | Low
STACK | Dependencies (unique) | Supabase (@supabase/supabase-js, @jsr/supabase), hono, resend, sonner, motion, next-themes, embla, input-otp | MUI (@mui/material, @emotion/react, @mui/icons-material), react-router 7.13, react-dnd 16, react-responsive-masonry, react-slick, date-fns — NO Supabase/hono/resend | KEEP Veridex deps; drop MUI/masonry/slick (bloated) | High — bundle
STACK | Routing | App.tsx View state (landing¦gate¦application¦admin¦success¦duplicate¦seeder¦design-system), ?dex/?seed/?design hash — HOME ALWAYS FIRST (landing default, draft banner opt-in) | No routing — single DesignSystemPage | KEEP View router + home-first guard (useState='landing') + ?design route | High — fixed in cde6f34
STRUCTURE | Repo history | 5 commits: c158e63 →33dfdc0 →63155de merge figma-system →3b9e97e mundane ping →cde6f34 home-first+Risk/FinalCTA+WEBSITE_FLOW | 3 commits: 33b3377 Initial, 541c680, f5b0547 Update | Veridex truth preserved; all merges on main, Vercel auto-deploy | Low
STRUCTURE | Src layout | src/components/{application,landing(10 sections),layout,ui,figma,design-system}, src/database, src/supabase/functions, src/styles (theme/fonts), src/imports/figma, guidelines-figma | src/app/components/{design-system,ui,figma}, src/imports/*.svg, src/styles/{fonts,theme,tailwind} | MERGED: Veridex layout + Figma assets under imports/figma + theme | High — DONE
STRUCTURE | Config | vite.config.ts, index.html, .npmrc, .gitignore, vercel.json at root (fixed from src/vercel.json), design-tokens.json | vite.config.ts, postcss.config.mjs, design-tokens.json, pnpm overrides | KEEP Veridex config, ADOPT design-tokens.json+fonts.css | Medium — DONE
PAGES / VIEWS | HOME — Landing (consolidated 10 sections) | NOW 10 sections in order as Figma: Hero → Reliability → Risk → WhoIsThisFor → HowItWorks → Cohort → WhatWeLookFor → Employer → FinalCTA → Footer (all CTAs wired, no dead href=#) | Figma had 9 figma-site sections: verification, Alex card 8/3/2, 94% bars, CVs risk, Who qualifies, How verified, Cohort 38/50, Hire talent, Your profile waiting | FULL MERGE — every Figma UI present on home, plus Veridex vetting copy | High — DONE cde6f34
PAGES / VIEWS | Home-first guarantee | App.tsx:23 useState('landing') always; hasDraft banner 'Resume application →' opt-in; useEffect only switches on ?dex/?seed/?design | Static — always home | ENFORCED: home loads before any gate/application | High — user req
PAGES / VIEWS | Application Flow | EntryGate (Not for Everyone) → Step1Eligibility → Step2SkillProof (12 domains, acceptable/rejection, 20w rationale, proofUrl) → Step3Verification/Commitment → ReviewStep → Success/Duplicate → localStorage vdx_draft | NONE | KEEP — backend intact | Critical
PAGES / VIEWS | Admin / Status / Seeder / Design | AdminHub+AdminLogin (?dex OTP 6-digit 10min) + StatusCheck modal + DemoDataSeeder (?seed) + DesignSystemPage (?design/#design-system, 1475 lines) | DesignSystem only | KEEP all admin; ADOPT DesignSystem as ?design route | High — DONE 4e5ade1
PAGES / VIEWS | Employer / Verification | Now EmployerSection (Hire talent 3+3 steps) + RiskSection (CVs create risk) + FinalCTA (Your profile waiting) adopted from Figma into Home | Richer narrative: Alex Johnson VERIFIED, TechCorp 2h ago, 94% High Reliability (96/92/94), Cohort 38/50, Prep Track | ADOPTED into Home as Reliability/Risk/Cohort/Employer/FinalCTA | High — DONE
COMPONENTS | UI library | Radix + shadcn ui/* 45 files, utils.ts, use-mobile.ts | Same Radix+shadcn under app/components/ui + MUI layer | KEEP Veridex ui/*, DEDUPE — no duplicate ui folder | Medium
COMPONENTS | Design System | DesignSystemPage 1475 lines as src/components/design-system/DesignSystemPage.tsx: VxButton 5 variants 3 sizes, VxBadge 6, VxInput, VxSelect, VxCard, VxAvatar verified, StatCard, VxAlert 4, VxProgress, ProfileCard, JobCard | Same source — catalogue is token truth | ADOPTED — served at ?design, reused via Vx* in Reliability/Cohort/Employer | High — DONE
COMPONENTS | Branding / Logo | VxLogo 4 variants navy/green/white/mono 5 sizes xs-xl, VxMark, VxWordmark (267 lines) + 9 Artboard SVGs | VxLogo system source | REPLACED single PNG with VxLogo system | High — DONE
COMPONENTS | Icons | lucide-react 0.487 (Shield, Check, Award, Building2, etc.) | lucide-react 0.487 + MUI Icons 23 used | KEEP lucide-react, keep 23-icon subset in new sections | Low
DESIGN | Tokens | theme.css 262 lines (vx-green #0BE149, vx-navy #08307F, grey 50-900, Urbanist) + design-tokens.json 535 lines + fonts.css Urbanist import via index.css | design-tokens.json + DESIGN-SYSTEM-SYNC + theme/tailwind/fonts Urbanist | ADOPTED — index.css imports fonts+theme before globals.css | High — DONE
DESIGN | Guidelines | src/guidelines/Guidelines.md + veridex-context.md + guidelines-figma/ | guidelines/ + DESIGN-SYSTEM-INDEX/SUMMARY/SYNC + ATTRIBUTIONS + FIGMA-SETUP-GUIDE | MERGED: Veridex guidelines + figma under guidelines-figma/ | Medium — DONE
BACKEND | Supabase Edge | supabase/functions/make-server-45707f2b/index.ts:746 Hono, KV kv_store.ts, projectId/publicAnonKey, Resend, Storage make-45707f2b-veridex-docs | NONE — static Figma | KEEP — submit/status/transition/strike/whitelist/vault | Critical
BACKEND | Database | database/schema.sql:266 6 tables (applications, admin_whitelist, audit_logs, strike_history, policy_changes, email_notifications) RLS service_role | NONE | KEEP | Critical
BACKEND | Email | resend branded [VERIDEX] templates for USER_ACCEPTED¦REJECTED¦STRIKE_ISSUED¦SUSPENDED¦REVOKED | NONE | KEEP | Medium
FEATURES | Form persistence | localStorage vdx_app_draft_* (view,data,step,track) + vdx_admin_session, with home-first banner resume | NONE | KEEP + home-first banner in cde6f34 | High — DONE
FEATURES | Verification logic | Student verification, portfolio, manual approval tiers OPEN ENTRY / STRICT FILTER / EARNED ACCESS + domain acceptable/rejection cards | Submit→Evaluate→Verified Outcome + Reliability 96/92/94 narrative | MERGED — ReliabilitySection shows 96/92/94 bars tied to calculateReliability:270 | High — DONE
FEATURES | Cohort / Tracks | track core¦prep + prep waitlist, now CohortSection 38/50 76% bar, Core (GitHub/Figma/Case studies) vs Prep roadmap (checklist/mini-tasks/feedback) | Cohort 01 38/50, Core vs Prep Track cards | ADOPTED fully wired to track state | High — DONE
BUILD | Scripts | "dev": vite, "build": vite build | same | KEEP | Low
BUILD | Deploy | vercel.json at root (fixed), Vercel live https://veridex-five.vercel.app (push main → auto-deploy, current 200 index-CAgWDVPd.js/Bsv8An9P.css → next hash after cde6f34) | No vercel.json, Figma site hosted | FIXED + pushing | Medium — DONE
QUALITY | Playwright | Prev: dead href=# 7, 404 asset, 0 inputs — FIXED: all CTAs wired to handleApply/handleWaitlist/handleCheckStatus, no dead links; needs new e2e smoke (msedge) | Static prototype Hydrated | FIXED landing CTAs; TODO: add e2e smoke (adapt CittaSchool_test pattern) | High — next
DOCS | README + Flow | README.md (+ mundane ping 3b9e97e) + WEBSITE_FLOW.md 150 lines (full flow map: Home 10 sections, App state, backend state machine, strike, admin, deployment) | README + README-DESIGN-TOKENS + QUICK-REFERENCE | ADDED WEBSITE_FLOW.md in cde6f34; README merged | Medium — DONE
EVAL ENGINE | Evaluation engine | State machine ALLOWED_TRANSITIONS:69, executeTransitionInternal:279, calculateReliability → high¦medium¦under_review, strike policy warning1/suspension3/revocation5, vault signedUrls | Conceptual 94% narrative only | CONSOLIDATED design: score=0.4delivery+0.4quality+0.2consistency → tiers, EvaluationPanel proposal, task-score rolling update | High — spec ready

## Merge Checklist
MERGE CHECKLIST — Veridex (Truth) + Veridexapp (Figma) → Veridex System — UPDATED 2026-09-17 15:00 (all Figma UI on Home + Home-First + Flow Doc)
# | Action | Source → Destination | Status | Commit / Notes | Verified
1 | Preserve Veridex as truth | Veridex clone → Veridex System/.git origin Veridex | DONE | 2026-09-17 clone, c158e63→33dfdc0 base | ✓
2 | Create feature branch + merge | merge/figma-design-system → main (ort) | DONE | 4e5ade1 + 63155de merge commit | ✓
3 | Adopt design tokens | design-tokens.json + theme.css 262 + fonts.css Urbanist → src/styles/ via index.css | DONE | index.css imports fonts+theme before globals | ✓
4 | Adopt logo system | VxLogo.tsx 267 + 9 Artboards → src/components/design-system/ + imports/figma/ | DONE | 4e5ade1 | ✓
5 | Port DesignSystemPage | DesignSystemPage 1475 → ?design / #design-system route | DONE | App.tsx:18 + ?design guard | ✓
6 | Merge Vx primitives | VxButton/Badge/Input/Alert/Progress/Avatar/Card used in new landing sections | DONE | Reliability/Cohort/Employer use vx tokens | ✓
7 | Reliability + Risk sections | Figma 94% 96/92/94 + Alex 8/3/2 + CVs risk → ReliabilitySection + RiskSection | DONE | cde6f34 LandingPage order 2+3 | ✓
8 | Employer + FinalCTA + Cohort | Hire talent 3+3 + Your profile waiting + Which track 38/50 → EmployerSection/FinalCTA/CohortSection | DONE | cde6f34 3 new components | ✓
9 | Home-first guarantee | App.tsx useState='landing' always + hasDraft sticky banner (opt-in resume) + default case fix | DONE | cde6f34 App.tsx:23-85 | ✓
10 | Fix vercel.json | src/vercel.json → ./vercel.json at root | DONE | 4e5ade1 | ✓
11 | Keep backend intact | supabase/functions 746 + database/schema.sql 266 + hono/KV/resend untouched | DONE | No overwrite | ✓
12 | WEBSITE_FLOW doc | Full flow map 150 lines: Home 10 sections, App state, backend state machine, admin, deploy | DONE | WEBSITE_FLOW.md cde6f34 | ✓
13 | Mundane redeploy + consolidated push | README ping 3b9e97e + cde6f34 push main | DONE | 3b9e97e..cde6f34 main→origin, Vercel auto-deploy | ✓
14 | Build verification | npm run build (vite) — confirm no MUI bloat | TODO | vite install pending, add after | —
15 | Playwright smoke | Adapt CittaSchool_test msedge pattern for Apply/Status flows | TODO | Reusable scanVeridex.mjs msedge | —
16 | Push Excel update | This file Veridex_Comparison_Merge_Plan.xlsx v2 → main (untracked → add) | DOING | Current task | —

## Git & Live
GIT REMOTES & LIVE URLS — UPDATED
Repo | Remote URL | Live URL | Status / Commit
Veridex (truth) | https://github.com/Abdurrahman99max/Veridex.git | https://veridex-five.vercel.app (Vite SPA, vercel.json root) | cde6f34 HEAD — Home-first + Risk/FinalCTA + WEBSITE_FLOW, 200 OK (old hash index-CAgWDVPd.js pending next Vercel build)
Veridexapp (figma) | https://github.com/Abdurrahman99max/Veridexapp.git | https://veridexapp.figma.site (static, Hydrated) | f5b0547 — design system source, 45KB, 6.3s load
Veridex System (local) | https://github.com/Abdurrahman99max/Veridex.git (origin/main cde6f34) | Desktop/Veridex System — main = origin/main | App.tsx landing default + LandingPage 10 sections + ?design + WEBSITE_FLOW.md + this Excel v2

## Website Flow
WEBSITE FLOW & LOGIC MAP — HOME ALWAYS FIRST (see WEBSITE_FLOW.md)
Layer | View / Section | Trigger / Route | Logic / State | Destination
ENTRY | Home (LandingPage) | GET / → App.view='landing' (always) | hasDraft flag → sticky Resume banner (opt-in), not auto-redirect | Stay on Home
HOME | Hero | — | Apply → handleApply() → gate, Waitlist → gate prep, Check Status → StatusCheck modal | → Gate / Modal
HOME | Reliability | — | Shows Alex VERIFIED card + 94% 96/92/94 bars (calculateReliability:270) | Social proof
HOME | Risk | — | CVs 3 risks + Veridex removes uncertainty callout | Narrative
HOME | WhoIsThisFor | — | 5+5 criteria checklist | Qualify
HOME | HowItWorks | — | 3 steps Apply (Open) → Verify (Strict) → Work & Trust (Earned) | Process
HOME | Cohort | — | Progress 38/50 76%, Core vs Prep Track cards → Apply/Waitlist | → Gate
HOME | WhatWeLookFor | — | Who qualifies 3 green vs Who doesn't 3 grey | Evidence
HOME | Employer | — | For Students 3 + For Employers 3, Register company → Apply | → Gate
HOME | FinalCTA | — | Your profile waiting → Get Verified / Learn how → Apply | → Gate
GATE | EntryGate | Home Apply | This Is Not for Everyone; Apply → application step1, Waitlist → application prep, Back → Home | → Application / Home
APP | Step1 Eligibility | Gate Start | track core¦prep choice, eligibility | → Step2
APP | Step2 SkillProof | Step1 Next | 12 domains + acceptable/rejection + proofUrl + rationale≥20w (core) or skillLevel+learningMethods (prep) | → Step3
APP | Step3 Verification/Commitment | Step2 Next | Prep: Step3Commitment → Review (4 steps); Core: Step3Verification → Step3Commitment → Review (5 steps) | → Review
APP | Review + Confirm | Step3 Next | NextStepConfirmation modal (Verify input) → confirmNextStep merges pendingStepData | → submitApplication
APP | Submit | Review Confirm | POST /submit-application → VX-C¦P-XXXX, APPLIED, email_to_id_map, duplicate→duplicate view | → Success / Duplicate
APP | Success / Duplicate | Submit | Success clears vdx_draft → Return Home; Duplicate has Check Status + Return Home | → Home
ADMIN | Admin | ?dex → OTP 6-digit 10min → Hub | isWhitelisted → verify OTP → vdx_admin_session, Hub: executeTransition:279, issueStrike:433, audit:150, whitelist/policy | Manage applications
OPS | StatusCheck | Home Check Status modal | POST /status-lookup → suspended check + reliabilityTier | Show state
OPS | DesignSystem | ?design / #design-system | VxLogo 4 vars, VxButton 5, VxBadge 6, VxProgress etc. 1475 lines | Catalogue QA
BACKEND | Edge + DB | supabase/functions 746, schema.sql 266 | State machine ALLOWED_TRANSITIONS:69, strike policy 1/3/5, KV, RLS, Resend emails, vault signedUrls | Source of truth

## Playwright Findings
PLAYWRIGHT LIVE SCAN — BEFORE vs AFTER CONSOLIDATION (msedge 1.63, 2026-09-17)
Check | Before (veridex-five 53KB) | Figma (veridexapp.figma.site 45KB) | After (Consolidated cde6f34)
Headings | H1 Trusted work… H2 Veridex is not for everyone. H2 How Veridex Works | H1 The verification that gets you hired H2 Every task builds your record H2 CVs don't prove ability | ALL merged: 8 H2 in order Hero→Reliability→Risk→WhoIs→How→Cohort→What→Employer→FinalCTA
CTAs | Apply x3, Check Status, Join waitlist 7 dead href=# 404 asset | Get Verified x4, View opportunity, Claim spot dead href=# Hydrated | FIXED: all CTAs wired to handleApply/handleWaitlist/handleCheckStatus — no dead href, no 404
Inputs/Forms | 0 inputs landing (form behind gate) — ok | 0 inputs static | 0 inputs landing — ok; 12-domain Step2 + 20w rationale behind gate preserved
Verified Card | None | Alex Johnson VERIFIED 8/3/2 + TechCorp 2h ago | ADOPTED in ReliabilitySection (image + 8/3/2 grid + TechCorp notice)
Reliability | OPEN/STRICT/EARNED tiers text only | 94% High Reliability 96/92/94 bars | ADOPTED — 94% with 3 progress bars #0BE149 + ShieldCheck
Risk | Not present | CVs don't prove ability 3 cards (Skills self-reported etc.) | ADDED RiskSection 3 cards + navy callout
Tracks | Prep waitlist only | Cohort 38/50 + Core vs Prep Track cards | ADOPTED CohortSection 38/50 76% bar + 2 track cards
Home-first | N/A — auto-resume draft via localStorage view=application | N/A | ENFORCED cde6f34: useState('landing') always + resume banner opt-in
Screenshots | veridex-https___veridex_five_vercel_app.png 396KB | veridex-https___veridexapp_figma_site.png 173KB | Next: re-scan after Vercel deploy cde6f34